School Development Plan Objectives for Citizenship : 2017-2019

| Aim: | Objective: | Target group(s); e.g. whole school, girls, boys, staff etc | Action: | Who’s Responsible? | Dates from and to: | Milestones/ progress |
| --- | --- | --- | --- | --- | --- | --- |
| To have a review of current practice of teaching and learning in Citizenship within each class. | To review practice within individual classes. | Whole school and staff | - Class leads audit their current practice using an audit tool. | Class leads | Jun 2017 – Dec 2017 | Audit tool made-June 2017 Audit completed July 2017 |
|  | To highlight areas for further development. |  | - Use the audit tool to assess and highlight areas for development. | MT | Dec 2017 – July 2018 | Audit assessment and collation started September 2017 November 2017 -Collation of data Assess areas for development |
|  | To investigate if a scheme of work would be beneficial, if lessons are intrinsic to whole school learning or if discrete lessons are required. |  | - SMT to discuss. | PD/LW | Jun 2017 – July 2018 | June 2017 -Downloaded DfE Citizenship programme of work for key stage 1 & 2 (non-statutory) and key stage 3 & 4 (mandatory). Copy given to classes. Carry out research |
| To have a review of Citizenship resources within school. | To audit resources. | Whole school and staff | - Centralise resources for Citizenship in the resource corridor. - Audit the resources for Citizenship throughout whole school. - Assess the audit tool to highlight areas that may need further resourcing. | MT | Jun 2017 - Dec 2017 | Audit tool made-June 2017 Audit started November 2017 |
|  | To audit if resources need staff training to enable use. |  | - Assess the audit tool to highlight general staff training and specific resource training ie. Cloth models. | MT | Jun 2017 – Dec 2017 | Audit tool made-June 2017 Audit started November 2017 |
| To develop a concise and updated policy for Citizenship which links to PSHE. | To review current policies and update where necessary, exploring if policies should be combined or independent with links to each other. | Whole school and staff | - Read the policies and update. - Consult the whole school staff on finished document. - Verify with Governing Body. | PD/LW/MT | Sep 2017 – Sep 2018 | Ongoing |